## Progress Planning and Tracking
Project Name: | AC-10: AI & Music
Report Date: | 2024-09-01
[5 empty] | Project Plan/SRS/SDD Submission | Testbed Development |  |  | Prototype Presentation |  |  | Testing & Reiteration |  |  | Final Report |  | C-Day
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2024-09-01 | 2024-09-08 | 2024-09-15 | 2024-09-22 | 2024-09-29 | 2024-10-06 | 2024-10-13 | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17 | 2024-11-24 | 2024-12-01
Project Plan & SRS | Meet with Faculty Project Owner (FPO) | 100% | Delayed but complete | Team | 2024-09-01: 4
| Define Requirements | 100% | Complete | Team | 2024-09-01: 4
| Review Requirements with SH | 100% | Complete | Team | 2024-09-01: 4
| Draft Project Plan & Software Requirements Specification (SRS) document | 100% | Complete | Team | 2024-09-01: 8
| Submit Project Plan & SRS for Approval | 50% | In Progress | Team | bar: 2024-09-01
Software Design Document (SDD) | Draft Software Design Document (SDD) | 100% | Complete | Team | 2024-09-01: 8
| Submit SDD for Approval | 50% | In Progress | Team | bar: 2024-09-01
| Training Design | 0% |  | Team | 2024-09-08: 12; 2024-09-15: 12
| Test Suite Design | 0% |  | Selam | 2024-09-08: 12; 2024-09-15: 12
MIDI Testbed for Model Training | Compile MIDI Files for Model Training | 0% |  | Joseph & Trey | 2024-09-22: 12
| Process & Extract Data | 0% |  | Joseph & Trey | 2024-09-22: 12
| Analyze Training Results | 0% |  | Selam | 2024-09-22: 6
Model Prototype | Implement Prototype per SDD | 0% |  | Joseph & Trey | 2024-09-29: 20; 2024-10-06: 20
| Prototype Version Control & Documention | 0% |  | Team | 2024-09-29: 2; 2024-10-06: 2
| Implement User Interface (UI) | 0% |  | Joseph & Trey | 2024-10-13: 20
| UI Version Control & Documentation | 0% |  | Team | 2024-10-13: 2
Model Test Data | Test Prototype | 0% |  | Selam | 2024-10-20: 4; 2024-10-27: 4; 2024-11-03: 4
| Debug & Update Prototype | 0% |  | Team | 2024-10-20: 16; 2024-10-27: 16; 2024-11-03: 16
Final Report | Presentation Preparation | 0% |  | Selam | 2024-11-10: 8; 2024-11-17: 2; 2024-11-24: 2; 2024-12-01: 2
| Jupyter Notebook Tutorial Publication | 0% |  | Joseph | 2024-11-10: 8; 2024-11-17: 2; 2024-11-24: 2; 2024-12-01: 2
| C-Day Poster Preparation | 0% |  | Team | 2024-11-10: 2; 2024-11-24: 2; 2024-12-01: 2
| Project Website Publication | 5% | In Progress | Team | 2024-10-27: 4; 2024-11-03: 4; 2024-11-10: 2
| Final Report Submission to D2L and FPO | 0% |  | Team | bar: 2024-11-17
|  |  | Total work hours | 279 | 30 | 24 | 24 | 30 | 22 | 22 | 22 | 20 | 24 | 24 | 20 | 5 | 6 | 6
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours